## Gantt Chart w % Complete
DataDive's Gantt Chart
Group Members: Harpreet Ghag, Micah Mercado, Xavier Mercado, Madhuri Pyreddy, Joshua Francisco, Michael Novella
| TASK NAME | START DATE | DAY OF PROJECT | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Week 1
| Research - Pick a Topic | 2020-03-03 | 3 | 2020-03-08 | 5 | 0 | 5 | ALL | 50%
| Gather Several Datasets | 2020-03-03 | 3 | 2020-03-08 | 5 | 0 | 5 | ALL | 50%
Week 2
| Data Cleaning | 2020-03-09 | 8 | 2020-03-15 | 7 | 0 | 6 | Madhuri, Xavier, Harpreet | 0%
| Data Structuring/Transform | 2020-03-09 | 8 | 2020-03-15 | 7 | 0 | 6 | Madhuri, Xavier, Harpreet | 0%
Week 3
| Data Visualization | 2020-03-16 | 15 | 2020-03-22 | 7 | 0 | 6 | Xavier, Joshua, Micah | 0%
| Descriptive Analysis | 2020-03-16 | 15 | 2020-03-22 | 7 | 0 | 6 | Madhuri, Michael, Micah | 0%
Week 4
| Prescriptive Analysis | 2020-03-23 | 22 | 2020-03-29 | 7 | 0 | 6 | Harpreet, Madhuri, Michael | 0%
| Predictive Analysis | 2020-03-23 | 22 | 2020-03-29 | 7 | 0 | 6 | Harpreet, Madhuri, Michael | 0%
Week 5
| Draft Proposal | 2020-03-30 | 29 | 2020-04-05 | 7 | 0 | 6 | ALL | 0%
| Report Creation | 2020-03-30 | 29 | 2020-04-05 | 7 | 0 | 6 | Micah, Michael, Joshua | 0%
| Analysis Visualization | 2020-03-30 | 29 | 2020-04-05 | 7 | 0 | 6 | Xavier, Joshua, Harpreet | 0%
Week 6 Spring Break!
| Rough Draft | 2020-04-06 | 36 | 2020-04-12 | 7 | 0 | 6 | Micah, Michael, Joshua | 0%
Week 7
| Rough Draft Feedback | 2020-04-13 | 43 | 2020-04-19 | 7 | 0 | 6 | Micah, Michael, Joshua | 0%
| Finishing Touches/2nd Rough Draft | 2020-04-13 | 43 | 2020-04-19 | 7 | 0 | 6 | Micah, Michael, Joshua | 0%
Week 8
| Final Draft Due | 2020-04-20 | 50 | 2020-04-26 | 7 | 0 | 6 | Micah, Michael, Joshua | 0%
| Add New Methods/Info If Needed | [6 empty] | ALL | 0%
Week 9
| New Final Draft, If New Methodology Added |  | 57 |  |  |  |  | ALL | 0%
Week 10
| PRESENTATION | 2020-05-05 | 64 | 2020-05-05 | 0 | 0 | 1 | ALL | 0%